## Cover
CloudMigrate.in
Cutover Runbook — Azure
Microsoft Azure · v1.0 · generated 21 Oct 2026
Purpose | Minute-by-minute plan for a migration wave cutover with go / no-go and rollback.
Customer
Project / programme
Prepared by
Reviewed by
Last updated
How to use | 1. Set the planned start time in cell C2 of the Cutover Plan sheet; start / end times calculate from durations.
2. Rehearse at least once and update durations with real timings.
3. Hold the go / no-go meeting with quorum; record the decision.
4. If a rollback trigger fires, switch to the Rollback Plan sheet immediately.
Reference | Target regions: Central India (Pune), South India (Chennai), West India (Mumbai)
Landing zone: Azure Landing Zones (CAF) — management groups, Azure Policy
Security baseline: Microsoft Cloud Security Benchmark / CIS Microsoft Azure Foundations
Template provided as-is for planning purposes. Validate vendor programme terms and service availability before relying on them.

## Cutover Plan
Planned start
Cutover start (edit) → |  | 2026-11-07 22:00
Step | Phase | Task | Owner | Duration (min) | Planned start | Planned end | Go/No-go gate | Status | Actual end | Rollback ref | Notes
1 | T-7 days | Confirm wave scope, owners, communications and change approval | Migration lead | 0 |  |  |  | Not started |  | RB-0
2 | T-2 days | Lower DNS TTLs to ≤ 300 s; confirm replication healthy and lag < threshold | Network lead | 0 |  |  |  | Not started |  | RB-0
3 | T-1 day | Final test migration / failover reviewed; known issues logged | Migration engineer | 0 |  |  |  | Not started |  | RB-0
4 | Go / no-go | Go / no-go meeting: readiness checklist, staffing, rollback owner present | Migration lead | 30 |  |  | GATE | Not started |  | RB-0
5 | Freeze | Announce outage; disable user access / put application in maintenance mode | App owner | 15 |  |  |  | Not started |  | RB-1
6 | Freeze | Stop application services and scheduled jobs on source | App support | 15 |  |  |  | Not started |  | RB-1
7 | Data sync | Confirm final replication / CDC sync; record source row counts and checksums | DBA | 30 |  |  |  | Not started |  | RB-2
8 | Data sync | Set source databases read-only | DBA | 10 |  |  |  | Not started |  | RB-2
9 | Cutover | Launch / promote target instances (Azure Migrate server migration / Azure Site Recovery) | Migration engineer | 30 |  |  |  | Not started |  | RB-3
10 | Cutover | Complete database switchover (Azure Database Migration Service / SQL Managed Instance link) | DBA | 30 |  |  |  | Not started |  | RB-3
11 | Cutover | Update connection strings, secrets and configuration | App support | 20 |  |  |  | Not started |  | RB-3
12 | Cutover | Switch DNS / load balancer to target | Network lead | 15 |  |  |  | Not started |  | RB-4
13 | Validate | Technical smoke tests (services up, ports, logs, monitoring) | Migration engineer | 20 |  |  |  | Not started |  | RB-4
14 | Validate | Data reconciliation: row counts, checksums, control totals | DBA + data owner | 30 |  |  |  | Not started |  | RB-4
15 | Validate | Business validation by key users | App owner | 45 |  |  | GATE | Not started |  | RB-4
16 | Decision | Go-live decision or rollback (before rollback deadline) | Migration lead | 15 |  |  | GATE | Not started |  | RB-5
17 | Go-live | Re-enable user access, scheduled jobs and integrations | App support | 15 |  |  |  | Not started
18 | Go-live | Communicate completion; open hypercare queue | Migration lead | 10 |  |  |  | Not started
19 | Hypercare | Monitor for 72 h; daily check-ins with owners | Ops lead | 0 |  |  |  | Not started
Total window (hours)

## Go-No-Go
Criterion | Owner | Met? | Evidence
Pre-migration checklist: all Critical items Done or N/A | Migration lead
Test migration / failover passed in the last 7 days | Migration engineer
Replication lag within threshold for 24 h | Migration engineer
Verified backup of source taken in the last 24 h | DBA
Rollback plan reviewed and rollback owner on call | Migration lead
Business owner and key users available for validation | App owner
Change approved and communications sent | Change manager
No open P1 / P2 incidents on dependent systems | Ops lead
Monitoring and alerting live on target | Ops lead
Security sign-off (exposure, access, logging) | Security lead

## Rollback Plan
Ref | Trigger | Rollback action | Owner | Duration (min) | Point of no return?
RB-0 | Pre-cutover readiness not met | Postpone wave; no changes made to production. | Migration lead | 0 | No
RB-1 | Unable to stop source services cleanly | Restart source services; re-open access; reschedule. | App support | 15 | No
RB-2 | Final sync incomplete or validation counts mismatch | Set source read-write; resume source; investigate replication. | DBA | 20 | No
RB-3 | Target launch or DB switchover fails | Abandon target; revert source to read-write; restore DNS. | Migration engineer | 30 | No
RB-4 | Smoke tests or business validation fail and can't be fixed in the window | Revert DNS / load balancer; re-enable source; capture target state for analysis. | Network lead | 30 | No
RB-5 | Go-live decision is no-go | Execute RB-4; if writes occurred on target, reverse-sync or replay per DB plan. | Migration lead | 60 | After go-live + writes: YES

## Contacts
Role | Name | Phone | Email | Backup
Migration lead
Rollback decision owner
DBA
Network lead
Application owner
Security lead
Azure support case