## Cover
CloudMigrate.in
Post-Migration Checklist — Azure
Microsoft Azure · v1.0 · generated 21 Oct 2026
Purpose | Validation and handover gate after each migration wave.
Customer
Project / programme
Prepared by
Reviewed by
Last updated
How to use | 1. Copy the Checklist sheet once per wave (or filter by wave in the Wave column).
2. Assign an owner and due date to every item; set Status from the drop-down.
3. Attach evidence links in the Evidence column — auditors and funding reviewers will ask.
4. The Summary sheet calculates completion by area; go-live needs every Critical item Done or N/A.
Reference | Target regions: Central India (Pune), South India (Chennai), West India (Mumbai)
Landing zone: Azure Landing Zones (CAF) — management groups, Azure Policy
Security baseline: Microsoft Cloud Security Benchmark / CIS Microsoft Azure Foundations
Template provided as-is for planning purposes. Validate vendor programme terms and service availability before relying on them.

## Summary
Area | Items | Done | In progress | Blocked | Not started | N/A | % complete
Functional validation
Performance
Data integrity
Security
Monitoring
Backup & DR
Cost & tagging
Operations handover
Decommission
Documentation
Business sign-off
Total
Go-live readiness rule: all Critical items Done or N/A, no Blocked items, ≥ 90% overall.
Critical items not yet Done

## Checklist
ID | Area | Item | Guidance | Azure tool / reference | Owner | Priority | Status | Due date | Wave | Evidence / notes
POST-001 | Functional validation | Application smoke tests passed | Log-in, key transactions, reports, integrations. | UAT scripts |  | Critical | Not started
POST-002 | Functional validation | End-to-end business process tested by the owner | Owner signs the result, not the project team. | UAT sign-off |  | Critical | Not started
POST-003 | Functional validation | Integrations and interfaces confirmed (inbound and outbound) | Payment gateways, SaaS, partners, file drops. | Integration register |  | Critical | Not started
POST-004 | Functional validation | Batch jobs ran successfully on schedule | Compare runtime with the source baseline. | Scheduler logs |  | High | Not started
POST-005 | Functional validation | Email / SMTP relay, printing and file shares working | Often forgotten until Monday morning. | Smoke tests |  | Medium | Not started
POST-006 | Performance | Key transaction response times within baseline tolerance | Typical tolerance ± 10%. | Azure Monitor, Log Analytics, Application Insights |  | High | Not started
POST-007 | Performance | Resource utilisation reviewed after 7 days | Right-size over- and under-provisioned resources. | Azure Monitor, Log Analytics, Application Insights |  | Medium | Not started
POST-008 | Performance | Database wait events / query performance reviewed | Compare top SQL with the source. | DB monitoring |  | High | Not started
POST-009 | Data integrity | Row counts and checksums reconciled | All tables or a signed sample for very large tables. | Validation scripts |  | Critical | Not started
POST-010 | Data integrity | Business control totals match (e.g. ledger balances) | Signed by finance or the data owner. | Reconciliation report |  | Critical | Not started
POST-011 | Data integrity | Replication / CDC stopped and source set read-only | Prevents split-brain writes. | Azure Database Migration Service / SQL Managed Instance link |  | Critical | Not started
POST-012 | Security | Security posture score reviewed for new resources | Microsoft Defender for Cloud (Defender CSPM, Secure Score) | Microsoft Cloud Security Benchmark / CIS Microsoft Azure Foundations |  | High | Not started
POST-013 | Security | No public exposure beyond design (ports, buckets, endpoints) | Scan external attack surface. | Microsoft Defender for Cloud (Defender CSPM, Secure Score) |  | Critical | Not started
POST-014 | Security | Logs flowing to central logging and SIEM | Microsoft Sentinel | Diagnostic settings to a central Log Analytics workspace; Activity Log export |  | Critical | Not started
POST-015 | Security | Privileged access reviewed; temporary migration access removed | Remove migration service accounts and keys. | Microsoft Entra ID with Privileged Identity Management and Conditional Access |  | Critical | Not started
POST-016 | Security | Encryption and key ownership verified | Azure Key Vault / Managed HSM with customer-managed keys | Azure Key Vault / Managed HSM with customer-managed keys |  | High | Not started
POST-017 | Monitoring | Alerts tested end-to-end (fire, route, acknowledge) | Azure Monitor, Log Analytics, Application Insights | Azure Monitor, Log Analytics, Application Insights |  | High | Not started
POST-018 | Monitoring | Dashboards published for the run team and owners | Azure Monitor, Log Analytics, Application Insights | Azure Monitor, Log Analytics, Application Insights |  | Medium | Not started
POST-019 | Backup & DR | First backups completed and a restore tested | Azure Backup with immutable vaults and soft delete | Azure Backup with immutable vaults and soft delete |  | Critical | Not started
POST-020 | Backup & DR | DR replication configured and failover test scheduled | Azure Site Recovery / zone-redundant services | Azure Site Recovery / zone-redundant services |  | High | Not started
POST-021 | Cost & tagging | All resources tagged per standard | CostCentre, Environment, Owner, Application, DataClassification | Azure Landing Zones (CAF) — management groups, Azure Policy |  | High | Not started
POST-022 | Cost & tagging | Cost allocated to the right cost centre in reports | Microsoft Cost Management, budgets, Azure Advisor | Microsoft Cost Management, budgets, Azure Advisor |  | Medium | Not started
POST-023 | Cost & tagging | Commitment / reservation candidates identified after 30 days | Azure Reservations, Azure savings plan for compute, Azure Hybrid Benefit | Microsoft Cost Management, budgets, Azure Advisor |  | Medium | Not started
POST-024 | Cost & tagging | Vendor funding evidence captured (tags, IDs, reports) | Subscription / account IDs, migration reports, customer attestation. | Funding tracker |  | High | Not started
POST-025 | Operations handover | Runbooks, RACI and SLAs accepted by the run team | Signed handover form. | Runbook & RACI |  | Critical | Not started
POST-026 | Operations handover | Patching and maintenance windows active | Azure Update Manager (Azure + Arc-enabled servers) | Azure Update Manager (Azure + Arc-enabled servers) |  | High | Not started
POST-027 | Operations handover | CMDB / asset register updated | Retire source CIs, add target CIs. | CMDB |  | Medium | Not started
POST-028 | Operations handover | Hypercare exit criteria met | No open P1 / P2, stable for 10 business days. | Hypercare log |  | High | Not started
POST-029 | Decommission | Source systems powered off after agreed retention period | Typically 2–4 weeks after successful cutover. | Decommission plan |  | High | Not started
POST-030 | Decommission | Source data securely wiped / media destroyed with certificate | Required for regulated data. | Destruction certificate |  | High | Not started
POST-031 | Decommission | Licences, support contracts and hosting released | Capture savings in the benefits tracker. | Contract register |  | Medium | Not started
POST-032 | Documentation | As-built architecture and network diagrams updated | Stored in the design repository. | Architecture repo |  | Medium | Not started
POST-033 | Documentation | Lessons learned captured for the next wave | Update runbook durations and risks. | Retrospective |  | Medium | Not started
POST-034 | Business sign-off | Application owner acceptance signed | Formal closure for the wave. | Sign-off form |  | Critical | Not started
POST-035 | Business sign-off | Benefits tracker updated (cost, performance, risk) | Feeds the business case review. | Benefits tracker |  | Medium | Not started