CloudMigrate.in

Proof of Concept Charter

Template with a worked example for Google Cloud

| Cloud | Google Cloud |
| --- | --- |
| Version | v1.0 — 21 Oct 2026 |
| Customer | [Customer name] |
| Owner | [Programme / migration lead] |

Template provided as-is. Replace bracketed text, delete guidance you do not need, and validate vendor programme terms before use.

# 1. Summary

| Field | Entry |
| --- | --- |
| POC title | BigQuery warehouse modernisation POC |
| Business sponsor | [Name, role] |
| Technical lead | [Name, role] |
| Start / decision date | [dd-mmm-yyyy] / [dd-mmm-yyyy] |
| Time box | 4–6 weeks |
| Environment | Isolated sandbox in Google Cloud with budget alerts and guardrails |

# 2. Business question and hypothesis

Business question: [What decision will this POC enable?]

Hypothesis (example): Moving the sales-analytics mart to BigQuery cuts month-end report runtime by 70% at equal or lower monthly cost.

# 3. Success criteria

Each criterion must be measurable and agreed by the sponsor before build starts.

| # | Criterion | Target | Measurement method | Result |
| --- | --- | --- | --- | --- |
| 1 | Query parity | 100% of 150 top queries return identical results | [How it will be measured] |  |
| 2 | Performance | Month-end batch ≤ 30% of current runtime | [How it will be measured] |  |
| 3 | Cost | Monthly cost ≤ current platform run-rate | [How it will be measured] |  |
| 4 | Security | Column-level security on PII columns enforced | [How it will be measured] |  |
| 5 | Adoption | Three business users rebuild their dashboards in Looker | [How it will be measured] |  |

# 4. Scope

In scope:

[Use cases / user journeys]

[Data sets and volumes]

[Integrations]

Out of scope:

Production cut-over

Full HA / DR (designed, not built)

[Other exclusions]

# 5. Architecture (POC)

Services (example): BigQuery, BigQuery Migration Service, Dataflow, Looker, Cloud Storage.

Guardrails: Cloud Foundation Fabric — resource hierarchy, organisation policies; Cloud Identity / Workforce Identity Federation with the corporate IdP; budgets and alerts; data classification applied to POC data; no production credentials.

# 6. Data

| Data set | Classification | Volume | Source | Handling |
| --- | --- | --- | --- | --- |
| [e.g. policy documents] | [Internal / Personal] | [GB / rows] | [System] | [Masked / synthetic / approved copy] |

# 7. Plan

| Week | Activities | Output |
| --- | --- | --- |
| 1 | Charter sign-off, environment, data access, test set | Signed charter, sandbox ready |
| 2–3 | Build minimum architecture | Working POC |
| 4 | Testing against criteria; user feedback | Results log |
| 5 | Cost model, production architecture | Production design and estimate |
| 6 | Read-out and decision | Go / no-go |

# 8. Roles

| Role | Name | Responsibility |
| --- | --- | --- |
| Sponsor |  | Owns the decision |
| Technical lead |  | Design and delivery |
| Data owner |  | Approves data use |
| Security |  | Approves guardrails |
| Users / testers |  | Evaluate outcomes |

# 9. Risks and assumptions

Data access approved by [date].

Test users available in week 4.

Vendor quotas / service availability in the target region confirmed.

[Other]

# 10. Funding

Rapid Migration and Modernization Program (RaMP) — Assessment, planning and migration support; credits

Committed use discounts — Discounted compute / database run-rate

Google Cloud Marketplace private offers — ISV software drawn down against commit

# 11. Decision record

| Decision | Rationale | Next steps | Signed (sponsor) | Date |
| --- | --- | --- | --- | --- |
| [Go / No-go / Extend] |  |  |  |  |

# 12. Sign-off

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Business sponsor |  |  |  |
| Technical lead |  |  |  |
| Security |  |  |  |