## Cover
CloudMigrate.in
Pre-Migration Checklist — Google Cloud
Google Cloud · v1.0 · generated 21 Oct 2026
Purpose | Readiness gate before each migration wave.
Customer
Project / programme
Prepared by
Reviewed by
Last updated
How to use | 1. Copy the Checklist sheet once per wave (or filter by wave in the Wave column).
2. Assign an owner and due date to every item; set Status from the drop-down.
3. Attach evidence links in the Evidence column — auditors and funding reviewers will ask.
4. The Summary sheet calculates completion by area; go-live needs every Critical item Done or N/A.
Reference | Target regions: asia-south1 (Mumbai), asia-south2 (Delhi)
Landing zone: Cloud Foundation Fabric — resource hierarchy, organisation policies
Security baseline: CIS Google Cloud Platform Foundation Benchmark
Template provided as-is for planning purposes. Validate vendor programme terms and service availability before relying on them.

## Summary
Area | Items | Done | In progress | Blocked | Not started | N/A | % complete
Governance & commercials
Discovery & assessment
Landing zone & identity
Network & connectivity
Security & compliance
Data & databases
Application readiness
Backup & DR
Testing
Cutover readiness
Communications
Operations readiness
Total
Go-live readiness rule: all Critical items Done or N/A, no Blocked items, ≥ 90% overall.
Critical items not yet Done

## Checklist
ID | Area | Item | Guidance | Google Cloud tool / reference | Owner | Priority | Status | Due date | Wave | Evidence / notes
PRE-001 | Governance & commercials | Executive sponsor and steering committee named | Sponsor owns the business case; steering meets fortnightly through migration. | Programme charter |  | Critical | Not started
PRE-002 | Governance & commercials | Business case approved with run-rate, migration cost and funding shown separately | Avoid double counting vendor credits against run-rate savings. | Cloud Billing reports, billing export to BigQuery, FinOps hub |  | Critical | Not started
PRE-003 | Governance & commercials | Vendor funding / programme approvals in place | Confirm eligibility, customer consent and evidence requirements before work starts. | Funding plan |  | High | Not started
PRE-004 | Governance & commercials | Billing account / subscription ownership agreed | Who holds the payer / billing root, who pays, and how chargeback works. | Cloud Billing reports, billing export to BigQuery, FinOps hub |  | High | Not started
PRE-005 | Governance & commercials | Commitment strategy agreed (post right-sizing) | Stage commitments after 30–60 days of post-migration telemetry. | Resource-based and spend-based committed use discounts, BigQuery editions commitments |  | Medium | Not started
PRE-006 | Governance & commercials | Change freeze and blackout calendar captured | Month-end, quarter-end, festive peaks, audits. | Wave plan |  | High | Not started
PRE-007 | Discovery & assessment | All in-scope servers discovered with ≥ 14 days of performance data | Size to p95, not allocation. | Migration Center discovery client |  | Critical | Not started
PRE-008 | Discovery & assessment | Application owners identified and interviewed | Every application needs a named owner who signs the disposition. | Application portfolio |  | Critical | Not started
PRE-009 | Discovery & assessment | Dependencies mapped and validated with owners | Include AD, DNS, NTP, SMTP, file shares, licensing servers, batch schedulers. | Migration Center discovery client |  | Critical | Not started
PRE-010 | Discovery & assessment | 7R disposition signed off per application | Retire, retain, rehost, relocate, replatform, repurchase, refactor. | Assessment workbook |  | High | Not started
PRE-011 | Discovery & assessment | Database inventory with versions, size, features and growth | Drives migration method and downtime estimate. | Database Migration Service (homogeneous + Oracle → PostgreSQL / AlloyDB) |  | High | Not started
PRE-012 | Discovery & assessment | Licensing position confirmed (BYOL / licence-included) | OS, database, middleware and ISV licences — including mobility rights. | Licence register |  | High | Not started
PRE-013 | Discovery & assessment | Data classification completed for in-scope data | Personal data under DPDP, regulated data (RBI / SEBI / IRDAI), confidential IP. | Data classification register |  | Critical | Not started
PRE-014 | Landing zone & identity | Landing zone deployed as code and peer reviewed | Cloud Foundation Fabric — resource hierarchy, organisation policies | Terraform (Cloud Foundation Fabric modules) |  | Critical | Not started
PRE-015 | Landing zone & identity | Guardrails enforced (allowed regions, encryption, tagging, public access) | Regions: asia-south1 (Mumbai), asia-south2 (Delhi). | Cloud Foundation Fabric — resource hierarchy, organisation policies |  | Critical | Not started
PRE-016 | Landing zone & identity | Identity federation and MFA for all administrators | Cloud Identity / Workforce Identity Federation with the corporate IdP | Cloud Identity / Workforce Identity Federation with the corporate IdP |  | Critical | Not started
PRE-017 | Landing zone & identity | Privileged access just-in-time and break-glass accounts tested | Two break-glass accounts, stored offline, alerting on use. | IAM groups with just-in-time access; IAP for SSH / RDP |  | High | Not started
PRE-018 | Landing zone & identity | Tagging / labelling standard published and enforced | Labels: cost-centre, env, owner, app, data-class | Cloud Foundation Fabric — resource hierarchy, organisation policies |  | High | Not started
PRE-019 | Network & connectivity | Private connectivity provisioned and tested for throughput | Size for replication peaks plus production traffic. | Cloud Interconnect (Dedicated / Partner) + HA VPN |  | Critical | Not started
PRE-020 | Network & connectivity | IP address plan with no overlap against on-premises | Reserve ranges for growth (containers, PaaS private endpoints). | IPAM |  | Critical | Not started
PRE-021 | Network & connectivity | Hybrid DNS resolution validated both directions | Cloud DNS with forwarding and peering zones | Cloud DNS with forwarding and peering zones |  | Critical | Not started
PRE-022 | Network & connectivity | Firewall rules for migrated apps prepared and reviewed | Least privilege; document every rule with an owner. | Shared VPC hub with Cloud NGFW / firewall policies |  | High | Not started
PRE-023 | Network & connectivity | Internet egress and inspection path designed | Centralised egress through the hub firewall. | Shared VPC hub with Cloud NGFW / firewall policies |  | High | Not started
PRE-024 | Network & connectivity | Load balancer / DNS TTLs lowered ahead of cutover | Lower TTLs to ≤ 300 s at least 48 h before cutover. | Cloud DNS with forwarding and peering zones |  | Medium | Not started
PRE-025 | Security & compliance | Security baseline enabled in every account / subscription / project | Security Command Center | CIS Google Cloud Platform Foundation Benchmark |  | Critical | Not started
PRE-026 | Security & compliance | Central logging with ≥ 180-day retention in India | CERT-In directions (April 2022). | Aggregated log sinks to a central logging project |  | Critical | Not started
PRE-027 | Security & compliance | Encryption at rest with customer-managed keys where required | Cloud KMS customer-managed encryption keys | Cloud KMS customer-managed encryption keys |  | High | Not started
PRE-028 | Security & compliance | Vulnerability scanning on target images and hosts | Security Command Center threat detection, Cloud IDS | Security Command Center threat detection, Cloud IDS |  | High | Not started
PRE-029 | Security & compliance | Incident-response runbook updated for cloud (6-hour CERT-In reporting) | Include contacts, evidence capture and regulator notifications. | IR runbook |  | High | Not started
PRE-030 | Security & compliance | DPDP obligations reviewed for in-scope personal data | Notice, consent, purpose limitation, safeguards, breach notification. | DPDP checklist |  | High | Not started
PRE-031 | Data & databases | Migration method chosen per database with downtime budget | Database Migration Service (homogeneous + Oracle → PostgreSQL / AlloyDB) | Database Migration Service (homogeneous + Oracle → PostgreSQL / AlloyDB) |  | Critical | Not started
PRE-032 | Data & databases | Schema / code conversion assessed for heterogeneous moves | Stored procedures, triggers, data types, collation and character set. | Database Migration Service (homogeneous + Oracle → PostgreSQL / AlloyDB) |  | High | Not started
PRE-033 | Data & databases | Data validation approach agreed (row counts, checksums, business reports) | Define pass criteria before migration. | Validation scripts |  | Critical | Not started
PRE-034 | Data & databases | Bulk data transfer method sized (online vs offline) | Storage Transfer Service / Transfer Appliance | Storage Transfer Service / Transfer Appliance |  | Medium | Not started
PRE-035 | Application readiness | Hard-coded IPs, hostnames and file paths identified | Search configs, scripts, ODBC / JDBC strings and scheduled tasks. | Code / config scan |  | High | Not started
PRE-036 | Application readiness | Certificates and secrets inventoried and migrated to a vault | Cloud KMS customer-managed encryption keys | Cloud KMS customer-managed encryption keys |  | High | Not started
PRE-037 | Application readiness | Third-party integrations and IP allow-lists notified | Banks, payment gateways, SaaS, partners that allow-list your egress IPs. | Integration register |  | Critical | Not started
PRE-038 | Application readiness | OS and runtime support validated on target | End-of-support OS flagged for remediation or ESU. | Compatibility matrix |  | Medium | Not started
PRE-039 | Application readiness | Batch jobs and schedulers mapped to new hosts | Cron, Control-M, SQL Agent, Windows Task Scheduler. | Batch inventory |  | High | Not started
PRE-040 | Backup & DR | Backup policies defined per tier and applied by default | Backup and DR Service | Backup and DR Service |  | Critical | Not started
PRE-041 | Backup & DR | RTO / RPO agreed per application and DR design approved | Regional / cross-region replication with Backup and DR Service | Regional / cross-region replication with Backup and DR Service |  | High | Not started
PRE-042 | Backup & DR | Pre-migration backup of every source system verified restorable | Your rollback depends on it. | Backup report |  | Critical | Not started
PRE-043 | Testing | Test plan and UAT scripts signed off by application owners | Functional, integration, performance and DR tests. | Test plan |  | Critical | Not started
PRE-044 | Testing | Performance baseline captured on source | Key transactions, batch runtimes, report durations. | Cloud Monitoring, Managed Service for Prometheus |  | High | Not started
PRE-045 | Testing | Test migration / test failover completed for the wave | Migrate to Virtual Machines | Migrate to Virtual Machines |  | Critical | Not started
PRE-046 | Cutover readiness | Cutover runbook rehearsed end-to-end | Timed rehearsal; update durations. | Cutover runbook |  | Critical | Not started
PRE-047 | Cutover readiness | Rollback triggers and decision owner agreed | Who calls rollback, at what time, on what evidence. | Cutover runbook |  | Critical | Not started
PRE-048 | Cutover readiness | Go / no-go meeting scheduled with quorum | Business, IT, security, vendor. | Go / no-go checklist |  | High | Not started
PRE-049 | Cutover readiness | Replication healthy and lag within threshold | Migrate to Virtual Machines | Migrate to Virtual Machines |  | Critical | Not started
PRE-050 | Communications | User and stakeholder communications sent | Outage window, what changes, who to call. | Comms plan |  | High | Not started
PRE-051 | Communications | Service desk briefed with known issues and FAQs | Temporary hypercare queue created. | ITSM |  | Medium | Not started
PRE-052 | Operations readiness | Monitoring and alerting configured on target before cutover | Cloud Monitoring, Managed Service for Prometheus | Cloud Monitoring, Managed Service for Prometheus |  | Critical | Not started
PRE-053 | Operations readiness | Patching schedule and maintenance windows defined | VM Manager OS patch management | VM Manager OS patch management |  | High | Not started
PRE-054 | Operations readiness | Runbooks and RACI handed to the operations team | Run-team shadows the final rehearsal. | Runbook & RACI |  | High | Not started
PRE-055 | Operations readiness | Cost budgets and anomaly alerts configured | Cloud Billing reports, billing export to BigQuery, FinOps hub | Cloud Billing reports, billing export to BigQuery, FinOps hub |  | Medium | Not started