## Cover
CloudMigrate.in
Discovery & Assessment Workbook — JioCloud
JioCloud · v1.0 · generated 21 Oct 2026
Purpose | Capture inventory, decide dispositions, plan waves and build the TCO.
Customer
Project / programme
Prepared by
Reviewed by
Last updated
How to use | 1. Populate Server Inventory from Azure Migrate (Jio-Azure targets) / agent-based discovery exports.
2. Complete the Application Portfolio with owners; score each app in the 7R Matrix.
3. Record dependencies to form move groups; assign waves in the Wave Plan.
4. Enter on-premises and target costs in TCO — totals and savings calculate automatically.
Reference | Target regions: In-country Jio data centres (including Jio-Azure regions in Jamnagar and Nagpur)
Landing zone: Sovereign landing zone — segregated environments, in-country keys and logging
Security baseline: CIS Controls v8 / ISO/IEC 27001:2022 / CSA CCM + DPDP, CERT-In, RBI, SEBI, IRDAI
Template provided as-is for planning purposes. Validate vendor programme terms and service availability before relying on them.

## Server Inventory
Server | Application | Environment | OS / version | vCPU | RAM (GB) | Storage (GB) | CPU p95 % | RAM p95 % | Target size | Disposition | Wave | Notes
APP-WEB-01 | Customer portal | Production | Windows Server 2016 | 4 | 16 | 200 | 38 | 61 |  | Rehost | W2 | Behind F5
APP-DB-01 | Customer portal | Production | Linux / PostgreSQL 13 | 8 | 64 | 1200 | 55 | 72 |  | Replatform | W2 | Managed PostgreSQL
FIN-ERP-01 | Finance ERP | Production | Oracle Linux 7 / Oracle 19c | 16 | 128 | 4000 | 47 | 80 |  | Rehost | W4 | Licence BYOL
HR-APP-01 | HRMS (legacy) | Production | Windows Server 2012 R2 | 2 | 8 | 120 | 6 | 25 |  | Repurchase | — | Replace with SaaS

## Application Portfolio
Application | Owner | Business criticality (1-5) | Data classification | Users | Change frequency (1-5) | Technical debt (1-5) | Disposition | Target JioCloud service | Complexity score | Wave | Notes
Customer portal | Head of Digital | 5 | Personal (DPDP) | 120000 | 4 | 3 | Replatform |  |  | W2
Finance ERP | CFO office | 5 | Confidential | 300 | 2 | 2 | Rehost |  |  | W4 | Month-end freeze
HRMS (legacy) | CHRO office | 3 | Personal (DPDP) | 2500 | 1 | 5 | Repurchase | SaaS |  | — | Contract ends Mar

## 7R Decision Matrix
Criterion | Weight | Rehost | Relocate | Replatform | Refactor | Repurchase | Retire / Retain
Speed to exit data centre | 0.25 | 5 | 5 | 3 | 1 | 3 | 5
Run-cost reduction | 0.2 | 2 | 2 | 4 | 5 | 4 | 3
Risk / complexity (5 = low risk) | 0.2 | 5 | 4 | 3 | 2 | 3 | 5
Business agility gained | 0.15 | 1 | 1 | 3 | 5 | 4 | 1
Skills available | 0.1 | 5 | 4 | 3 | 2 | 4 | 5
Licence impact | 0.1 | 3 | 3 | 4 | 4 | 3 | 5
Weighted score
Adjust weights per application class; weights should total 1.0.
Weight total

## Dependencies
Source application | Source server | Target application | Target server | Port | Protocol | Direction | Criticality | Move group | Validated by owner?
Customer portal | APP-WEB-01 | Customer portal | APP-DB-01 | 5432 | TCP | Outbound | High | MG-01 | Yes
Finance ERP | FIN-ERP-01 | Active Directory | DC-01 | 389 | TCP | Outbound | High | Shared | Yes

## TCO (3-year)
Cost line (INR) | Year 1 | Year 2 | Year 3 | Total | Notes
ON-PREMISES
Hardware refresh / depreciation | 0 | 0 | 0
Data-centre space, power, cooling | 0 | 0 | 0
Software licences & support | 0 | 0 | 0
Operations staff (allocated) | 0 | 0 | 0
Network / connectivity | 0 | 0 | 0
DR site | 0 | 0 | 0
On-premises total
JIOCLOUD TARGET
Compute (after right-sizing) | 0 | 0 | 0 |  | Term commitments in INR; connectivity bundles
Storage & backup | 0 | 0 | 0
Databases / PaaS | 0 | 0 | 0
Network, egress, connectivity | 0 | 0 | 0 |  | Jio MPLS / internet leased line / SD-WAN private connectivity
Security & monitoring services | 0 | 0 | 0
Licences (BYOL / included) | 0 | 0 | 0
Managed services | 0 | 0 | 0
Cloud total (run-rate)
ONE-TIME
Migration services | 0 | 0 | 0
Dual-running during migration | 0 | 0 | 0
Vendor funding / credits (enter as negative) | 0 | 0 | 0 |  | Keep separate from run-rate
One-time total
NET SAVING (on-prem − cloud − one-time)

## Wave Plan
Wave | Applications | Servers | Databases | Start | Cutover date | Downtime window | Rollback deadline | Lead | Status
W1 (pilot) | Intranet, file share | 4 | 0 |  |  | Sat 22:00–02:00 | Sun 01:00 |  | Not started
W2 | Customer portal | 6 | 1 |  |  | Sat 22:00–04:00 | Sun 02:00 |  | Not started