## Cover
CloudMigrate.in
Managed Services Runbook, RACI & SLA — OCI
Oracle Cloud Infrastructure · v1.0 · generated 21 Oct 2026
Purpose | Define who does what, how fast, and how the service is measured.
Customer
Project / programme
Prepared by
Reviewed by
Last updated
How to use | 1. Tailor roles to your organisation in the RACI sheet.
2. Agree SLA targets and escalation contacts before transition.
3. Use the Operational Runbook as the schedule of recurring tasks.
4. Review KPIs monthly in the service review.
Reference | Target regions: India West (Mumbai), India South (Hyderabad)
Landing zone: OCI Landing Zone (CIS-aligned) — compartments, policies
Security baseline: CIS Oracle Cloud Infrastructure Foundations Benchmark
Template provided as-is for planning purposes. Validate vendor programme terms and service availability before relying on them.

## RACI
Activity | Customer IT lead | Application owner | CloudMigrate service manager | CloudMigrate L1/L2 ops | CloudMigrate L3 architect | Security lead | Vendor support
Incident detection & triage | I | I | A | R | C | I | C
Major incident management | A | C | R | R | R | C | C
Problem management / RCA | I | C | A | R | R | C | C
Standard change execution | I | I | A | R | C | I | I
Normal change approval (CAB) | A | C | R | C | C | C | I
OS patching | I | C | A | R | C | I | I
Database patching | I | C | A | R | R | I | C
Backup monitoring | I | I | A | R | I | I | I
Restore requests & tests | C | R | A | R | C | I | I
DR drills | A | R | R | R | R | C | C
Security alert triage | I | I | A | R | C | R | I
Vulnerability remediation | C | C | A | R | R | R | I
Access requests & reviews | A | R | R | R | I | C | I
Capacity & performance management | I | C | A | R | R | I | I
Cost optimisation / FinOps | A | C | R | R | R | I | I
Commitment / reservation management | A | I | R | C | R | I | I
Landing-zone policy changes | A | I | R | C | R | C | I
Network & firewall changes | A | C | R | R | R | C | I
Certificate renewals | I | C | A | R | I | I | I
Monthly service review | A | C | R | C | C | C | I
Regulatory evidence & audits | A | C | R | R | C | R | I
R = Responsible · A = Accountable (exactly one) · C = Consulted · I = Informed

## SLA Matrix
Priority | Definition | Response | Restore target | Update frequency | Hours
P1 | Production down or security incident with data at risk; no workaround. | 15 min | 4 h | Every 30 min | 24×7
P2 | Production degraded or a critical function unavailable; workaround exists. | 30 min | 8 h | Every 2 h | 24×7
P3 | Non-critical function impaired or single user affected. | 4 h | 3 business days | Daily | Business hours
P4 | Request, question or cosmetic issue. | 1 business day | 10 business days | On resolution | Business hours

## Operational Runbook
Task | Frequency | OCI tool | Procedure summary | Owner | Evidence
Review overnight alerts and backup jobs | Daily | OCI Monitoring, Logging Analytics, Ops Insights; Autonomous Recovery Service / Object Storage backups with retention rules | Check failed jobs, re-run, raise incidents for repeated failures. | L1 ops | Daily ops log
Security findings triage | Daily | Cloud Guard and Security Zones; Logging Analytics / partner SIEM | Triage new high / critical findings within 24 h; assign owners. | Security analyst | SIEM case notes
Patch deployment | Monthly (+ emergency) | OS Management Hub / Fleet Application Management | Pilot ring → production rings; verify compliance ≥ 95% within 14 days. | L2 ops | Patch report
Restore test | Monthly | Autonomous Recovery Service / Object Storage backups with retention rules | Restore a tier-1 system to an isolated network; verify application start. | L2 ops + app owner | Restore test record
Cost review | Monthly | OCI Cost Analysis, Budgets, Cost Reports | Idle resources, right-sizing, commitments coverage, anomalies; actions with owners. | FinOps lead | Cost review deck
Access review | Quarterly | OCI IAM identity domains federated to the corporate IdP, MFA | Review privileged roles and remove stale access. | Security lead | Signed review
DR drill | Semi-annual | Data Guard / Full Stack Disaster Recovery | Planned failover of a tier-1 service; measure RTO / RPO. | L3 architect | DR report
Architecture / well-architected review | Quarterly | OCI Landing Zone (CIS-aligned) — compartments, policies | Review reliability, security, cost, performance and operations; update backlog. | L3 architect | Review report
Certificate expiry check | Weekly | Certificate inventory | Renew certificates expiring in < 30 days. | L2 ops | Cert register
Log retention verification | Quarterly | OCI Logging and Audit with Service Connector to central buckets | Confirm ≥ 180-day in-country retention and immutability. | Security lead | Retention evidence

## Escalation Matrix
Level | Role | Name | Phone | Email | Escalate after
L1 | Service desk / NOC |  |  |  | —
L2 | Platform engineer on call |  |  |  | 30 min (P1)
L3 | Lead architect |  |  |  | 1 h (P1)
L4 | Service delivery manager |  |  |  | 2 h (P1)
L5 | Account executive / customer CIO |  |  |  | 4 h (P1)

## Monthly KPIs
KPI | Target | Actual | Trend | Commentary
P1 response within SLA | 100%
P2 restore within SLA | ≥ 95%
Patch compliance (14 days) | ≥ 95%
Backup success rate | ≥ 99%
Restore tests passed | 100%
Security posture score | + trend
Critical findings > 30 days | 0
Commitment coverage | ≥ 70%
Unallocated (untagged) spend | < 5%
Changes causing incidents | < 2%